## Color
8-bit platform game - Man v. Martian
Final Year Project |  |  |  | Legend: | Task |  |  |  |  | Meeting |  |  |  |  | Deliverable |  |  |  |  | Milestone
Mark Daly
Project Start Date: | 2021-09-27 |  |  |  | March | [6 empty] | April | [34 empty] | May
Scrolling Increment: | 180 | time axis 2022-03-26 to 2022-05-20
Milestone description | Category | Progress | Start | Days | time axis 2022-03-26 to 2022-05-20
Week 1
Project Brief | Deliverable |  | 2021-09-27 | 1
Kick-off Meeting | Meeting |  | 2021-09-28 | 1
Gather inspiration from different games | Task |  | 2021-09-29 | 3
Brainstorm ideas | Task |  | 2021-10-02 | 2
Week 2
Trip to London with Peers | Milestone |  | 2021-10-04 | 2
Find out what is involved | Task |  | 2021-10-06 | 2
Project Scope | Deliverable |  | 2021-10-08 | 2
Gantt Chart | Deliverable |  | 2021-10-10 | 1
Week 3
Update Project Brief | Deliverable |  | 2021-10-11 | 1
Weekly Meeting | Meeting |  | 2021-10-12 | 1
Research Game Architecture | Task |  | 2021-10-13 | 1
Compare Python Frameworks | Task |  | 2021-10-14 | 3
Explain Framework Choice | Deliverable | 50% | 2021-10-17 | 1
Week 4 No weekly meeting (Jason out)
Explain Framework Choice | Deliverable | 100% | 2021-10-18 | 1
Two Player Research | Task |  | 2021-10-19 | 1
Learn Godot fundamentals | Task |  | 2021-10-20 | 3
Start Dodge the Creeps tutorial | Milestone |  | 2021-10-23 | 1
Create Player scene | Task | 66% | 2021-10-23 | 2
Week 5
Create Player scene | Task | 100% | 2021-10-25 | 1
Weekly Meeting | Meeting |  | 2021-10-26 | 1
Create Enemy scene | Task |  | 2021-10-27 | 3
Player-Enemy Interaction | Task |  | 2021-10-30 | 2
Week 6
Outline Document | Deliverable |  | 2021-11-01 | 3
Bi-weekly Meeting | Meeting |  | 2021-11-02 | 1
Game interface | Task |  | 2021-11-04 | 4
Week 7
Start Platformer tutorial | Milestone |  | 2021-11-08 | 1
Create Player scene | Task |  | 2021-11-08 | 3
Add floor | Task |  | 2021-11-11 | 1
Physics Layers | Task |  | 2021-11-12 | 1
Player Movement | Task |  | 2021-11-13 | 1
Jump Input | Task |  | 2021-11-14 | 1
Week 8
Injury to wrist | Milestone |  | 2021-11-15 | 7
Bi-weekly meeting (missed in hospital) | Meeting |  | 2021-11-16 | 1
Week 9
Function to calculate player velocity | Task |  | 2021-11-22 | 2
Create Enemy scene | Task |  | 2021-11-24 | 3
Player-Enemy Interaction | Task |  | 2021-11-27 | 2
Week 10
Optimise Camera | Task |  | 2021-11-29 | 1
Bi-weekly meeting | Meeting |  | 2021-11-30 | 1
Create Level | Task |  | 2021-12-01 | 1
Create Coin scene | Task |  | 2021-12-02 | 3
End of Semester 1 | Milestone |  | 2021-12-03 | 1
Christmas Recess
Create Portal scene | Task |  | 2022-01-10 | 1
Teleportation between levels | Task |  | 2022-01-11 | 3
Design 4 different levels | Task |  | 2022-01-14 | 3
Week 11
Start to Semester 2 | Milestone |  | 2022-01-17 | 1
Design title and end screens | Task |  | 2022-01-17 | 4
Score and deaths | Task |  | 2022-01-21 | 2
Pause Menu | Task |  | 2022-01-23 | 1
Week 12
Debug Game | Task |  | 2022-01-24 | 1
Learn How to Deploy Godot Projects | Task |  | 2022-01-25 | 1
Upload Projects to GitHub | Task |  | 2022-01-26 | 1
Learn about Godot Git Plugin | Task |  | 2022-01-27 | 1
Add ReadMe files | Task |  | 2022-01-28 | 2
Upload game executables as Releases | Task |  | 2022-01-30 | 1
Week 13
Setup Project repository | Task |  | 2022-01-31 | 1
Create Player Scene with dummy sprite | Task |  | 2022-02-01 | 2
1st Meeting of Semester 2 | Meeting |  | 2022-02-03 | 1
Use a dummy tileset to add a floor for the player | Task |  | 2022-02-04 | 3
Week 14
Setup physics (collision) layers | Task |  | 2022-02-07 | 1
Player Movement and Direction | Task |  | 2022-02-08 | 2
Calculate velocity and jump | Task |  | 2022-02-10 | 2
Player Animation | Task |  | 2022-02-12 | 2
Week 15
Create Enemy scene | Task |  | 2022-02-14 | 1
Add Camera, deactivate enemies outside view | Task |  | 2022-02-15 | 1
Create Bullet scene | Task |  | 2022-02-16 | 1
Bi-weekly meeting | Meeting |  | 2022-02-17 | 1
Add player shoot functionality | Task |  | 2022-02-17 | 2
Enemy bullet detection and death | Task |  | 2022-02-19 | 2
Week 16
Begin Game Design (Halt development) | Milestone |  | 2022-02-21 | 1
Research Design & Compare Drawing Software | Task |  | 2022-02-21 | 2
Learn Aseprite Tools and Layer Options | Task |  | 2022-02-23 | 1
Draw batch of Doughnuts (practice) | Task |  | 2022-02-24 | 2
12 Principes of Animation | Task |  | 2022-02-26 | 1
Doughnut Monster animation | Task | 50% | 2022-02-27 | 1
Week 17
Doughnut Monster animation | Task | 100% | 2022-02-28 | 1
Learn how to Design your own character | Task |  | 2022-03-01 | 1
Create Player Sprite (Idle Frame) | Task |  | 2022-03-02 | 5
Bi-weekly meeting | Meeting |  | 2022-03-03 | 1
Extended Abstract | Deliverable | 40% | 2022-03-06 | 2
Week 18
Extended Abstract | Deliverable | 100% | 2022-03-07 | 3
Learn about Walk/Run animation cycle | Task |  | 2022-03-10 | 1
Create Player Run Animation | Task |  | 2022-03-11 | 3
Week 19
Create Player Run Animation | Task |  | 2022-03-14 | 1
Create Enemy sprite (idle frame) | Task |  | 2022-03-15 | 3
Bi-weekly meeting | Meeting |  | 2022-03-18 | 1
Enemy move animation | Task |  | 2022-03-18 | 3
Week 20
Update character sprites in Godot | Task |  | 2022-03-21 | 1
Learn how to make basic and intermediate tilesets | Task |  | 2022-03-21 | 1
Create tileset | Task |  | 2022-03-22 | 3
Choose tileset colours to complement characters | Task |  | 2022-03-25 | 1
Add background layers | Task |  | 2022-03-26 | 2
Create and update simple bullet sprite in Godot | Task |  | 2022-03-27 | 1
Week 21
Create new stage template in Godot | Task |  | 2022-03-28 | 1
Presentation video and abstract | Deliverable |  | 2022-03-29 | 2
Add bullet direction (inheritence from player) | Task |  | 2022-03-31 | 2
Draw doorway sprite and create new scene in Godot | Task |  | 2022-04-02 | 2
Week 22
Amazon Coding Assessment and Science Ball | Task |  | 2022-04-04 | 1
Teleportation between levels | Task |  | 2022-04-05 | 1
Add in-game music | Task |  | 2022-04-06 | 1
Open Day | Meeting |  | 2022-04-06 | 1
Design title screen | Task |  | 2022-04-07 | 2
End of Semester 2 | Milestone |  | 2022-04-08 | 1
To add more data, Insert new rows ABOVE this one